## SD Phase
LIST OF DESIGN REQUIREMENTS & DELIVERABLES
SCHEMATIC DESIGN PHASE (SD)
SD General Requirements |  | Submittal Required
Review program specifications upon receipt of authorization to begin work.
Attend planning conferences to receive instruction from the District.
Secure project planning information including information on U/G utilities and site constraints.
Request any additional data needed from District.
Submit listing of proposed consultants planned for the project.
Coordinate project with other District projects.
Consult with the campus, consulting architect, and campus landscape architect regarding the project when directed by the District.
Design the facility in accordance with all applicable codes and standards.
Participate in DSA collaborative process (Fire-Life-Safety, Structural, ADA Accessibility) prior to 75% SD submittal
Obtain approval of SD work in progress from District's CMPCT team.
Modify or redesign the project as necessary to secure approval from the campus, validation from CMPCT, and approval from DSA.
Request and obtain approval from the Project Manager before initiating any work to modify the project documents which may require performance of extra services.
SD Architectural Requirements
Site Civil and Landscape Drawings (Scale: Minimum 1 inch = 40 feet)
▲ Depict overall dimensions of proposed new or altered building(s).
▲ Depict and identify existing structures within a radius of 300 feet of project site. Indicate distances from proposed new buildings to adjacent existing buildings, property lines, and roadways.
▲ Depict major new exterior elements and, for alterations and additions, existing exterior elements that will remain in place. Show streets, service drives, easements, loading docks, parking areas, paved areas, walks, stairs, ramps, pools, retaining walls, fences, fire hydrants, above & below ground storage (dry & wet), and equipment.
▲ Depict proposed finished elevations of building entrances and major exterior elements.
▲ Depict existing and proposed contours at one-foot intervals. Indicate method of general site drainage. Provide a written narrative on design grading and retention systems proposed. Discuss possible alternate systems.
▲ Provide sections through the site as needed to explain changes in levels within the proposed building as related to the site.
▲ Depict placement of ramps and other provisions for disabled access to the site and building.
▲ Depict landscape design.
▲ Depict site demolition.
▲ Show locations of existing utilities and proposed new utilities work.
▲ Document finding and design impacts from initial site investigations, geotechnical, and environmental reports.
Floor Plans (Scale: Minimum 1/4 inch = 1 foot)
▲ Indicate locations, room names, sizes (in assignable square feet), and space numbers for all programmed spaces and required gross area spaces including entrances, lobbies, corridors, stairs, elevators, toilet rooms, janitors' closets, and mechanical/electrical equipment rooms.
▲ Indicate overall dimensions of major elements of the building.
▲ Indicate building elements: walls, columns, doors, windows, openings, and major built-in equipment.
▲ Indicate compliance with applicable disabled access codes.
▲ Provide demolition plan if demolition required. Indicate existing work to be removed, and existing work to remain in place.
Elevations and Sections (Scale: Minimum 1/16 inch = 1 foot)
▲ Show all building elevations. Depict floor-to-floor dimensions, overall building height, and relationship to natural and graded ground contours.
▲ Include sections as needed to explain the structure and its design features.
Code Analysis Report & Plans
Provide a narrative discussion and summary of building code issues, impacts and restrictions particular to this project. The outline shall include a written report and diagrammatic plan drawings delineating design criteria (e.g. exit paths, travel distances, required exits, rated walls, rated corridors, building occupancy, construction type, and fire zones). The analysis shall be updated for each design phase.
Interdisciplinary Coordination Review
Provide a narrative discussion of methodology used to segregate structural, mechanical electrical and plumbing systems. Describe any zoning or hierarchies used.
Building Materials and Massing
▲ Provide display board with mounted samples of actual proposed exterior materials.
▲ Provide study models as needed to analyze various alternative building site locations and building massing schemes.
▲ Provide narrative description of the design concept and important features of the Project.
Basis of Design Report (Building Envelope)
Provide analysis of at least two alternate building envelope solutions as part of the initial 75% progress SD review.
SD Structural Requirements
Provide detailed written description of recommended structural system and the basis for recommending this system over other approaches.
Provide conceptual foundation and structural framing plan of a typical floor. Indicate via a dimensioned grid reference system, columns, load-bearing walls, shear walls, footings, and related items.
SD Plumbing Requirements
Provide written analysis of calculated load demands of proposed new plumbing systems, the design demand of the project, and the capacity of the existing plumbing systems, if any. Show sanitary systems, natural gas, domestic water, storm retention and release, and fire protection sub-systems.
Provide analysis of male and female fixture count and location with a comparison to plumbing code minimum requirements.
Provide plumbing plans with diagrammatic water service, storage, roof drainage, fire risers if applicable, and invert elevations at points of connection with site utilities.
SD HVAC Requirements
Provide written analysis of calculated loads of proposed new HVAC systems, and description of recommended system with the basis of recommendation over other approaches..
Provide a conceptual single-line mechanical diagram showing major ducts and equipment. Identify sizes and locations of major equipment items including cooling towers, chillers, pumps, fans, air-handling units, compressors, and related items.
Determine capacity of existing systems, if any, based on an examination of the facility's record drawings, an inspection of the existing system, and test reports.
Provide description of proposed fume hood ducting and exhaust system.
Show air intake and exhausts and demonstrate how air entrainment is avoided.
SD Electrical & Telecom Requirements
Provide site plan showing proposed method of service for electrical power, telecommunications, and fire alarm systems
Provide single-line diagram showing:
▲ Method of service (campus or local utility)
▲ Major transformers and transformer substations
▲ Major switchboards, motor control centers, and panel and distribution boards
▲ Major components of emergency power
▲ Major components of telecommunications system:
▲▲ Building Distribution Facility (BDF)
▲▲ Intermediate Distribution Facility (IDF)
▲▲ Proposed point of connection to campus backbone
▲▲ Narrative on proposed system design, media type conduit routing and access
SD Estimated Project Construction Cost
Provide estimate of the total construction cost of the Project. Estimates for building projects shall be arranged in CSI Uniformat detailed to Level 2.
Provide written narrative explaining in detail any deviation from the initial project budget. Be prepared to present program or design adjustment alternatives for District consideration when adjustments are needed to bring the project scope, project schedule, and construction budget into alignment.
Bring any unusual cost item to the attention of the District's Project Manager.
SD Project Schedule
Develop a simple project schedule identifying the following items. This schedule shall be reviewed with the Project Manager at all project meetings and updated by the Architect at each submittal.
▲ Project phase submittals (from Project Assignment)
▲ Review times assumptions
▲ Submittal dates for District Team review and submittal of CMPCT items
▲ CMPCT meeting date
▲ Plan submittal (from Project Assignment)
▲ Back check submittal (from Project Assignment)
▲ Pre-bid operations
▲ Construction duration
▲ Furnishing/installation of Group II equipment
▲ Commencement of operations/classes
SD Basis of Design Reports
Prepare a schematic phase Basis of Design Report for the following systems:
▲ Building Envelope and Structural Systems
▲ HVAC
▲ Building Automation, HVAC Controls and Building Metering
▲ Lighting
▲ Fire Suppression and Alarm
▲ Plumbing
▲ Provide documentation to the of interdisciplinary coordination review using clash detection software, such as rivet.
Provide preliminary LEED® check list identifying possible points for the building (for LEED® projects).
Provide preliminary energy model/Title 24 report for the building (The energy budget shall exceed the current Title 24 requirements by at least 20% for the existing building and 15% for major renovations).
Provide preliminary daylight model of the proposed building.
Provide preliminary renewable power calculations indicating approximate kW and kWh capacity proposed for the building.
Provide preliminary water calculations for the proposed building.
SD Area Calculations (JCAF 31)
At 100% SD submittal, provide a summary using Job Cost Accounting Form (JCAF) 31 to compare the area allocation in the Program specifications presented in the capital outlay request with the area allocations in the SD. Summary must include the total assignable area, total gross area, and resulting percentage efficiency of the design.
Develop a space-by-space comparison of the SD documents' ASF with the project program's ASF. These tabulations shall be made by floor and program component and include totals for the building or renovated area as a whole.
Provide a detailed written explanation of any major deviations from the area allocations in the program specifications presented in the capital outlay request.
SD Presentation to CMPCT
Architect shall make a progress SD presentation to District Team early enough in the development of the phase (approximately 75%) so that design comments from this review meeting can be effectively incorporated into the final 100% SD submittal for CMPCT approval. Submittal requirements include:
▲ The latest approved Physical Master Plan (available from District)
▲ A colored 'presentation' site plan, showing the shape and location of adjacent improvements, landscaping, shadows, and paving patterns
▲ A plan of each floor
▲ All elevations
▲ Sections necessary to show basic structural and vertical space organization
▲ A colored rendering perspective view, cast to provide a single overall view of the project from eye level. Samples of the rendering style shall be submitted to the Project Manager for approval prior to beginning rendering.
▲ A color photograph of the project site taken from a vantage point approximating that of the rendering.
▲ An estimate of the total construction costs
▲ Basis of Design reports for building envelope and Structural Systems; HVAC; Building Automation; HVAC Controls and Building Metering; lighting; Fire Suppression and Alarm; Plumbing; documentation of interdisciplinary review.
Adjust and complete SD incorporating comments received from the District team.
Prepare the following Presentation Materials for CMPCT Meeting:
▲ Provide in .JPG format on CD-ROM electronic image files of above items (except for cost estimate and Basis of Design reports). (.JPG format shall be sized with an image area exclusive of titles and borders of 1024 x 768 resolution or greater.)
▲ Provide a display board of the project rendering. Rendering shall be mounted on a rigid, non-warping base.

## DD Phase
LIST OF DESIGN REQUIREMENTS & DELIVERABLES
DESIGN DEVELOPMENT PHASE (DD)
DD Architectural Requirements
Site, Civil, and Landscape Drawings (Scale: minimum 1 inch = 40 feet)
Depict overall dimensions of proposed new or altered building(s). Indicate all references to a benchmark and a baseline. Indicate distances from each proposed new building to existing buildings, property lines, and roadways.
Depict existing structures within a radius of at least 300 feet of the project. Identify all structures and streets by name.
Depict new exterior elements and all existing exterior elements that will remain in place after an alteration or addition. Show streets, service drives, easements, loading docks, parking areas, paved areas, walks, stairs, ramps, retaining walls, fences, fire hydrants, and equipment.
Depict elevations of building entrances and major exterior elements.
Provide a site plan indicating existing and proposed contours at one-foot intervals. Indicate method of general site drainage. Provide a written narrative on proposed design grading and retention systems, and hydrology calculations. Discuss possible alternative solutions.
Provide sections through the site as needed to explain changes in levels within the proposed building as related to the site.
Depict the placement of ramps and other provisions for disabled access to the site and building. Identify the parking area and drop-off location nearest the building. Show the path of travel and indicate travel distances to all building entrances.
Provide a site utilities plan that depicts existing utilities, including underground lines, located within the project and proposed new utility services. Indicate the points of connection between new work and existing utility systems.
Provide a site demolition plan indicating existing structures and utilities that are to be removed either by the construction contractors or by others.
Provide landscape design drawings with plant and tree selections, pedestrian and green space features, hardscaped design, patterns and details to explain the concept.
Floor Plan (Scale: minimum 1/4 inch = 1 foot)
Indicate locations, room names, sizes (in assignable square feet), and space numbers for all programmed spaces and required gross areas including entrances, lobbies, corridors (with widths), stairs, elevators, toilet rooms, janitors' closets, and mechanical/electrical equipment rooms. Floor plans for additions or alterations to existing buildings shall show existing floor plan and indicate existing space usage and any proposed changes.
Indicate locations of all doors (showing door swings) and windows.
Indicate overall dimensions of the major elements of each building.
Indicate locations and fire ratings of fire separations, exit enclosures, fire doors, and similar elements.
Indicate provisions for making facilities accessible to and usable by the disabled. Indicate accessible toilets and drinking fountains.
Indicate location of plumbing fixtures such as lavatories, floor drains, water closets, urinals, service sinks, drinking fountains, eyewash fountains, deluge showers, and fire-hose cabinets.
Indicate principal built-in features such as fixed auditorium seats, kitchen equipment, display cases, counters, shelves, lockers, laboratory benches, casework, glass washers, sterilizers, fume hoods, and similar items.
Provide a plan depicting locations of movable furniture including "interior landscape" partitions and equipment. Differentiate between movable and built-in furniture and equipment. Clearly identify items not in contract (NIC).
Provide demolition plan if required by the project.
Provide reflected ceiling plans, to include lighting layouts, ceiling systems and design elements such as soffits, troughs, vaults, and coffers.
Provide a roof plan showing associated equipment, slopes, ridges, drains, roof access, equipment hoists, and other items.
Elevations and Sections (Scale: minimum 1/8 inch = 1 foot)
Depict all building elements including penthouses, entrances, windows, doors, stairs, platforms, louvers, vents, exhaust stacks, retaining walls, and similar items. Indicate proposed finished grades.
Indicate overall building and floor-to-floor heights.
Include sections as needed to explain the structure or its design features, including longitudinal and transverse sections for each major area, indicating floor elevations, existing and proposed exterior grades, ceiling heights, pipe tunnels, unexcavated areas, basement areas, rooflines, and parapets. Where appropriate, show connections to adjoining buildings.
Cross-reference sections and elevations to floor plans.
Indicate provisions for HVAC distribution and hood venting.
Interior Details (Scale: minimum 1/4 inch = 1 foot)
Provide detail plans, sections, and elevations for classrooms and lecture halls, kitchens and related service areas, laboratories and laboratory support areas, toilet and locker rooms, and other areas of special design.
Schedules
Provide a door schedule indicating each door's type, size, frame, rating assembly, material, hardware group and pertinent comments.
Provide a window schedule denoting size, type, frame, glazing, window covering, if applicable, and special comments.
Provide a preliminary interior finish schedule indicating the material, texture, and color of each finish material proposed for use in the project. Include finish of floor, floor base, wall and ceiling.
Material Boards
Provide samples of all finish materials listed in the materials/color schedule. Samples shall be accurate with respect to the actual finishes, textures, and colors being proposed. Materials samples shall be mounted and displayed on presentation boards for review and approval by the District. Proposed proprietary materials must allow for equal products to be substituted.
Code Analysis Report & Plans
Update the Code Analysis Report & Plans previously developed. Update shall document and illustrate the code implications of design development changes, and requirements arising from outside agency reviews (e.g. DSA interpretations).
DD Structural Requirements
Provide a structural plan for each level of the structure at the same used for the architectural plans. Foundation and framing plans based on load calculations and seismic analysis. Indicate columns, load-bearing walls, shear walls, footing, and related items via a dimensioned grid reference system.
DD Plumbing Requirements
Site Utilities Plan (Scale: minimum 1 inch = 40 feet)
Indicate routing of proposed new external utilities from each new building to each point of connection to the campus utility system - including fire service, sanitary systems, natural gas, domestic water, storm retention and release. Indicate all utility lines that are to be abandoned, removed, or rerouted.
Show all existing utilities within the project site based on the information provided by the District and by Architect's field investigations.
Floor Plans (Scale: minimum 1/8 inch = 1 foot)
Indicate all piping on the floor-level plan in which it will be installed, including diagrammatic water service, storage, roof drainage, fire risers (if applicable), and invert elevations at points of connection with site utilities, including sizes based on calculations.
Indicate locations of main waste lines and stacks and vents as well as all service mains, including those for water, air, gas, and vacuum.
Indicate all pieces of equipment - including pumps, tanks, generators, pressure-reducing valves, etc - showing their locations and required piping connections.
DD HVAC Requirements
Floor Plans (Scale: minimum 1/8 inch = 1 foot)
Indicate sizes and location of each piece of equipment including air-handling units, chillers, cooling towers, pumps, converters, expansion tanks, boilers, fans, fan coil units, and other equipment.
Provide double line mechanical plan showing primary duct layout, indicating all mains for each duct system.
On single line plan, indicate typical supply and return air zones for each type of occupancy, including the terminal unit with associated branch ducts and air outlets and inlets.
Indicate the typical exhaust air duct for each type of application; identify size and bottom of duct elevations of primary service ducts. Application types include: hoods, toilet rooms, janitors' closets, transformers, mechanical/electrical equipment rooms, and other rooms as required for a satisfactory indoor environment. A typical duct shall include an air inlet and a source destination for exhaust air.
Equipment schedules
Enlarged Mechanical Plans (Scale: minimum 1/4 inch = 1 foot)
Provide a layout of all equipment rooms to ensure that the proposed equipment will fit in the allotted space.
DD Electrical & Telecom Requirements
The power, signal, and telecommunications layouts shall be shown on one set of drawings, and lighting layouts shall be shown on a different set of drawings. Use standard symbol conventions.
Floor Plans (Scale: Minimum 1/8 inch = 1 foot)
Provide a site electrical plan, indicating method of service for electrical power, telecommunications, and fire alarm systems.
Provide a single-line electrical distribution diagram showing primary service to substations and secondary service to distribution switchboards, motor control centers, and panel boards for power and lighting. Show the permanent and temporary points of connection to external utilities such as high-voltage, telephone, and all signal systems.
Indicate each load center unit substation, motor control center, distribution switchboard, telecommunications equipment room, and closet.
Provide lighting plan for each type and location of lighting fixtures in typical offices, laboratories, corridors, examination rooms, and similar spaces, and use a schedule for detail.
Indicate major components of telecommunications system, including:
▲ Building Distribution Facility (BDF)
▲ Intermediate Distribution Facility (IDF)
▲ Point of connection to campus backbone. Indicate conduit number and size. Indicate size and locations of vaults.
▲ Coordinate information with site utilities plan.
▲ Narrative on proposed system design, media type conduit routing and access
Enlarged Equipment Room Plans (Scale: minimum 1/4 inch = 1 foot)
Provide a layout of all equipment rooms to ensure that proposed equipment will fit in the allotted space.
DD Outline Specifications
Prior to developing DD outline specifications, Architect shall meet with District and Project Manager to review specification guidelines. Attendees shall include Architect, Architect's consultants, and Architect's specification writer.
DD outline specifications shall include the following:
An index showing divisions and sections intended to be used in CSI format.
▲ A general description of the construction, including the structural system; wall, ceiling, roofing, and waterproofing systems; exterior and interior finishes; and doors, windows, and case work. These descriptions shall include applicable code references.
▲ A general description of the plumbing and HVAC systems including controls, ducts, filtration, and piping. These descriptions shall include applicable code references.
▲ A general description of electrical services including the voltage and number of feeders. The specifications shall provide a specific description of items to be served by emergency power and shall describe design considerations for special areas. This description shall include applicable code references.
▲ A general description of fire safety mechanical and electrical systems and devices required by the State Fire Marshal for the intended occupancy of the building.
▲ A description of special systems including laboratory control systems, energy management systems, and special exhaust systems.
DD Estimated Project Construction Costs
Provide updated estimate of the total construction cost of the projects. Estimates for building projects shall be arranged in CSI Uniformat detailed to Level 3, and summarized in a 2-7 format.
Provide written narrative explaining in detail any deviation from the approved estimated construction cost.
Bring any unusual cost item to the attention of the Project Manager.
DD Area Calculations
At 100% DD submittal, revise the area summary comparing the area allocations in the approved program and approved SD plans using Job Cost Accounting Form (JCAF) 31 to compare the area allocation in the Program specifications presented in the capital outlay request with the area allocations in the SD. Summary must include
DD Interdisciplinary Coordination Review
Provide an update to the Interdisciplinary Coordination Check (IDC) for the SD phase documents using clash detection software such as rivet (BIM).
DD Soils and Materials Testing
Make initial recommendations for construction phase testing and special inspections such as soils and materials testing, welding inspections, and dewatering requirements.
DD Basis of Design Reports
Submit updated Basis of Design Reports for all systems. Updates should clearly indicate any changes proposed to the systems, and any revisions to performance characteristics that have been discovered through the DD process.
Provide updated LEED® check list confirming possible points for the project. Provide LEED® forms updated with information for all the possible LEED® points for the building (for LEED® projects).
Provide updated energy model/Title 24 report for the building.
Provide updated daylight model of the proposed building.
Provide updated renewable power calculations in kW and kWh proposed for the building.
Provide updated water calculations for the proposed building.
DD Response to District Comments
Provide written response to all comments from Constructability Review performed by Project Manager.
Provide written response to all comments from CMPCT.

## CD Phase - 50%
LIST OF DESIGN REQUIREMENTS & DELIVERABLES
CONSTRUCTION DOCUMENTS PHASE (CD) -- 50%
Architectural Drawings
Title Sheet: Indicate index, general notes, legends, and a small-scale site and project location map. Plan notes shall not include General Condition items. Notes must coordinate with and conform internally within the document set.
Site plan
Life/Safety plans, including applicable code analysis and tabulations
Key, reference and enlarged floor plans
Roof plan
Reflected ceiling plans showing all penetrations
Demolition plan (when appropriate)
Exterior elevations and sections
Furniture and equipment plans, where applicable
Wayfinding, signage plans, where applicable
Interior and casework elevations
Partition, ceiling, and design feature details
Schedules: door, window, and interior finishes
▲ Other schedules as appropriate
Enlarged wall sections
Stair and elevator plans, sections and details, where applicable
Updated materials board
Finish and Furniture Sample Binders
Civil Drawings
Existing civil survey
Site plan
Over excavation, grading and drainage plan
Site profile sections
Details
Composite site utilities plan
Horizontal control plans
Site demolition plan
Structural Drawings
Plans and sections: Indicate location, type of member, size, and material of each structural element for foundations, framing, floors, roofs, and any intermediate levels
Schedules: framing, beam and column
Details of connections, special assemblies, and expansion, drift and seismic joints
Details of structural framing systems required to support nonstructural components and equipment.
Develop Storm Water Pollution Prevention Plan.
Plumbing Drawings
Site utility sewer lines sized with invert elevations at points of connection
Building waste line layouts, sized with vent stacks and connections to drains, fixtures and equipment
Building hot and cold water supply layouts, sized with circulation mains, tanks, branches, risers and connections to fixtures and equipment.
Riser diagrams for supply and waste systems
Fire-extinguishing equipment, risers and standpipes, where applicable
Plumbing fixtures, tanks, and pumps with drainage and supply connections
Locations and sizes of natural gas, vacuums and medical gas systems, where applicable.
Detail sections demonstrating coordination of structural, HVAC, and piping systems
HVAC Drawings
Schedules and legends
Floor plans, sections indicating air and piping systems including all branch distribution
Sections, details and enlarged floor plans depicting layout of mechanical equipment rooms
Air and piping systems, including all branches, on each floor plan
Air balance schedule for outside, supply, return, and exhaust air for each air system; sections demonstrating sufficient clearances and volumes for air flows and access of equipment, where applicable.
Flow diagrams for chilled water, condenser water, and boilers, where applicable
Air riser diagram for each type of system
Plans and detail sections depicting the complete HVAC systems and branches with duct and pipe sizes for heating, steam, refrigeration, exhaust and ventilation, where applicable
Auxiliary HVAC required for 24/7 operating equipment service systems, where applicable
Electrical / Telecommunications Drawings
Electrical service to the building from public utility, with size of feeders
Site and building transformer locations and their connections
Main switchboard power panels, light panels, and associated equipment
Feeder and conduit sizes
Site and building light fixtures, receptacles, switches, and power outlets
Telecommunications system design including point and nature of connection to existing service, BDF's, IDF's, conduit routing, outlets, cabling/wiring, terminal cabinets, and backboards. Show coordination with supporting mechanical services and with site utilities plans.
Complete fire alarm system including its connection to existing system, where applicable
Emergency electrical power system including generator, transfer switches, fuel tanks, and all auxiliaries
Audio Visual Equipment
Landscape Drawings
Finished grading plan
Irrigation plan
Irrigation details
Planting plan
Planting details
Hardscape (paving) plan
Hardscape details (walls, walks, planters, etc.)
Specifications
In conjunction with construction management and District staff, develop Division 1 project special conditions, for review with project team, including multi-prime delivery method.
Statement of Sustainable Design
Documentation of compliance with California Energy Code.
Statement demonstrating application of environmentally responsible design.
Cost Estimate
Provide an updated estimate using the same estimation method and building component format as used in DD Phase.
Code Analysis Report & Plans
Provide an update of the code analysis report & plans, documenting and illustrating the code implications of all design development and changes, and any requirements arising from outside agency reviews. Provide a narrative discussion on corrections made arising from reviews.
Interdisciplinary Coordination Review
Provide an updated interdisciplinary coordination check
Reponses on Owner's Comments
Provide a written response to all comments.

## CD Phase - 90%
LIST OF DESIGN REQUIREMENTS & DELIVERABLES
CONSTRUCTION DOCUMENTS PHASE (CD) - 90%
Note: At the 90% completion phase, plans shall be submitted as 100% complete. Consultant drawings shall be coordinated with architectural and reconciled with a quality assurance review. Notes must coordinate with, and conform to, the written contract documents. Products and materials specified on the drawings must be identical to the products and materials required in the written contract documents and specifications. The 90% completion designation is solely to acknowledge that the plans have not been plan checked. In addition to the documents listed for the 50% CD submittal, the following items shall be submitted at 90%:
Architectural Drawings
Detail the anchorage of all fixed equipment in accordance with the California Building Standards Code, Title 24, CCR, all applicable parts
Structural Drawings
Structural drawings shall be accompanied by computations, stress diagrams, and other pertinent data and shall be complete to the extent that the calculations for individual structural members can be readily interpreted. Computations shall be prefaced by a statement outlining the basis for the structural design and indicating the manner in which the proposed building will resist vertical loads and horizontal forces. Computations shall be sufficiently complete as to establish that the structure will resist the loads and forces prescribed by the CCR, Title 24, all applicable parts. Assumed safe bearing pressures on soils and the ultimate strengths of concrete shall be provided in computations and noted on drawings. Where unusual conditions occur, any additional data that are pertinent to the work shall be submitted.
Plumbing Drawings
All plumbing drawings shall indicate the complete plumbing system in detail and shall include methods for fastening equipment to the structure to resist seismic forces.
HVAC Drawings
All HVAC drawings shall indicate the complete heating, ventilating, and air-conditioning systems in detail and shall include methods for fastening equipment to the structure to resist seismic forces.
Electrical/Telecommunication Drawings
Electrical drawings shall indicate all components of the electrical and telecom system in place and connected to the sources of services. Provide sufficient level of detail to illustrate connections, routings, and other items in complex areas. All wiring shall be final-sized. Indicate detailed methods for fastening equipment to the structure to resist seismic forces. Indicate the following:
▲ Feeder and conduit sizes
▲ Schedule of feeder breakers or switches
▲ Locations of light fixtures, receptacles, switches, power outlets
▲ All circuits
▲ Complete telecommunication system design to accommodate terminal resources to be provided separately by campus. Show point and nature of connection to existing service. Show BDF's, IDF's, terminal racks/cabinets and/or backboards. Show conduit routing, cabling/wiring and outlets.
▲ Complete Audio Visual system design
Stamped Drawings and Specifications
Stamp all drawings, calculations and specifications as required by law by a duly licensed architect and/or engineer.
Materials Board
Submit final updated materials board.
Basis of Design Reports
Submit updated Basis of Design Reports for all systems. The update should clearly indicate any changes proposed to the systems and any revisions to performance characteristics that have been discovered through the design process.
Provide final LEED® check list identifying possible points for the project. Provide final LEED® forms updated with information for all the possible LEED® points for the building (for LEED® projects).
Provide final energy model/Title 24 report for the project. Provide final daylight model of the proposed building.
Provide final renewable power in kW and kWh proposed for the project.
Provide final water calculations for the proposed building.
Contract Documents
The District will prepare the front end bidding documents, and will make all project documents available to the public during the bid process. Architect is responsible for submitting the following documents to the Project Manager:
▲ Certification Page
▲ Project Description
▲ Index to Specifications
▲ Specifications, Division 1 - special conditions, if any
▲ Specifications, Divisions 2 through 16
▲ List of Drawings, with dates
▲ Appendices, keyed to their respective CSI section, which list the following:
▲▲ Named manufacturers
▲▲ Required submittals
▲▲ Required warranties exceeding 12 months
▲▲ Required spare parts
▲▲ Required tests and inspections
▲▲ Tests and inspections to be paid for by contractor
Estimated Project Construction Cost
Provide updated estimates of the total construction cost of the project at 90%. Estimates shall be arranged in CSI Uniformat detailed to Level 4, and summarized in a 2-7 format.
The 90% cost estimate shall include materials quantities and unit prices. Estimates shall include itemized cost breakdowns of all work activities on the project; these breakdowns will be used to establish the format used by the Contractor in applying for progress payments.
Compare the 90% cost estimate with the construction budget. Any significant differences between the revised estimates and the construction budget shall be brought to the immediate attention of the Project Manager.
Provide written narrative explaining in detail and deviation from the approved estimated construction cost.
Calculation of Areas
Provide an area summary comparing the area allocations in the approved program and approved SD and DD plans with the 100% CD plans. The summary should include changes to the total assignable area, the total gross area, and the resulting building efficiency.
Soils and Materials Testing
Include a list of requirements for special testing and inspections, such as soils and materials testing, welding inspections, and dewatering requirements, to be conducted during the construction phase, as specified in Divisions 1 through 16 of the contract documents.
Interdisciplinary Coordination Review
Provide interdisciplinary coordination check (IDC) drawings (hard copy and electronic files)
Agency Plan Review Submittals
Obtain approval of the CDs from the required plan check reviewers:
▲ DSA: Fire / Life / Safety
▲ DSA: Access Compliance Review
▲ DSA: Structural
▲ Third-parties: Building Code Compliance, Seismic, Constructability
▲ Local Health Department Reviews: Projects with swimming pools and/or food service facilities will require submittal to local city/county health department. Coordinate requirements with Project Manager, as needed.

## CD Phase - 100%
LIST OF DESIGN REQUIREMENTS & DELIVERABLES
CONSTRUCTION DOCUMENTS PHASE (CD) - 100%
Contract Documents
100% plans and specifications shall incorporate all review comments and shall be stamped/signed off as approved by the review agencies, including DSA, District, etc.
Certify, by a signed statement on the drawings and by provision of required calculations, that the CDs comply with the energy conservation standards set forth in Title 24.
Stamp all drawings and specifications as required by law for registered architects and engineers.
Submit three (3) full-size sets and one (1) 11x17 set of completed, wet-stamped and signed construction documents to the Project Manager.
Provide on CD-ROM the same items in their electronic equivalents. Verify current software versions are acceptable to the Project Manager prior to transmitting electronic files.
Estimated Project Construction Costs
Provide final updated estimates of the total construction cost of the project, arranged in CSI Uniformat and detailed to Level 4.
The final 100% cost estimate shall include materials quantities and unit prices as well as itemized cost breakdowns of all work activities on the project.
The final 100% cost estimate shall be revised and updated from the 95% cost estimate to reflect any changes in the design of the Project as well as all revisions made to the CDs after the 90% submittal.
Compare the final 100% cost estimate with the construction budget. Any significant differences between the revised estimates and the construction budget shall be brought to the immediate attention of the Project Manager.
Provide a written narrative explaining in detail any deviation from the approved estimated construction cost.
Responses to District Comments
Provide a written response to all comments from the District/Project Manager.